## Sheet1
Fleet Management Project Planning
Id | Task Name | Duration | Start | Finish | Predecessors | Resource Names
0 | Fleet Management project planning | 113 days? | Thu 1/3/19 | Mon 6/10/19
1 | Kick off | 1 day | Thu 1/3/19 | Thu 1/3/19
2
3 | Requirement Specification | 41 days | Fri 1/4/19 | Fri 3/1/19 | 1 | Célestin,DJilo Lauris
4
5 | Vehicule tracking | 71 days? | Mon 3/4/19 | Mon 6/10/19
6 | Configurer le serveur traccar | 5 days | Mon 3/4/19 | Fri 3/8/19 | 3 | DJilo Lauris,Marcel
7 | Prise en main des trackeur GPS | 5 days | Mon 3/11/19 | Fri 3/15/19 | 6 | Marcel,DJilo Lauris
8 | Achat du module traccar de Odoo | 1 day | Wed 3/13/19 | Wed 3/13/19 | 7FS-3 days
9 | Configuration du module traccar dans Odoo | 10 days | Mon 3/18/19 | Fri 3/29/19 | 7 | DJilo Lauris,Marcel
10
11 | Release Geofencing and remote vehicule controle | 15 days | Mon 4/1/19 | Fri 4/19/19
12 | Envoie d'une commande d'arrêt / démarage par SMS | 5 days | Mon 4/1/19 | Fri 4/5/19 | 9 | DJilo Lauris,Marcel
13 | Arrêt d'un véhicule lorsqu'il sort de sa zone | 5 days | Mon 4/8/19 | Fri 4/12/19 | 9 | DJilo Lauris,Marcel
14 | Creation du trajet / zone d'un véhicule | 5 days | Mon 4/15/19 | Fri 4/19/19 | 13 | DJilo Lauris,Marcel
15 | Arrêt d'un vehicule sortie de sa zone | 2 days | Mon 4/15/19 | Tue 4/16/19 | 13 | DJilo Lauris,Marcel
16
17 | Release First Beta Version | 1 day? | Mon 4/22/19 | Mon 4/22/19 | 11 | Célestin,DJilo Lauris,Marcel
18
19 | Release Fleet Inventory Management | 15 days? | Mon 4/22/19 | Fri 5/10/19 | 11 | DJilo Lauris,Marcel
20
21 | Release Reporting (to be detail) | 20 days? | Mon 5/13/19 | Fri 6/7/19 | 19 | Célestin,DJilo Lauris,Marcel
22
23 | Release Version 1.0 | 1 day? | Mon 6/10/19 | Mon 6/10/19 | 21 | Célestin,DJilo Lauris,Marcel